## 1 GIA
Gender impact assessments
Table 1 - Gender impact assessments progress
Required | Required | Required | Required | Required | Required | Recommended | Recommended
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
Accessibility Corporate Faciltiies | Service | We undertook an Accessibility Audit in August 2021 to ensure our corporate facilities are physically accessible to all our visitors. | For Review | Yes | We have ensured the channels our customers use for their enquiries and interaction with us, and their identified gender, are captured in the development of our new Customer Relationship Management system. We introduced multiple non-gendered toilets at our Gateway Road (Warrnambool) office through appropriate change management conversations. We included COVID-19 QR code check-ins at different heights at our corporate facilities. | Yes | Intersectionality was considered and while data is collected on multiple demographics as part of our engagement approach, the way it's collected makes it challenging to analyse to consider intersectionality in depth.
Ripple Effect Grants Program | Program | The Ripple Effect program provides grants that support projects and initiatives in our local community, make a significant and positive change, and represent great value for money. We prioritise support for community-based, not-for-profit organisations across our service region. Grants are assessed against four themes: regional prosperity; education, training and volunteering; health and wellbeing; and natural environment. | For Review | Yes | We updated the Ripple Effect program guidelines to indicate that those projects addressing gender equity may be given priority in our grant assessment. We reviewed and updated the gender-related questions in our grant application form. In our 2022 grant information session with successful applicants, we raised awareness of gender equity issues and set expectations for outcomes measurement in project reporting (e.g. number of participants per gender). We embedded gender equity awareness and criteria into the onboarding process for our assessment panel. We established a reporting baseline of project outcomes and gender data from our 2021/22 grant round, and enhanced our capacity to include gender analysis in our annual program reporting. | Yes | Intersectionality was considered and while data is collected on multiple demographics as part of our engagement approach, the way it's collected makes it challenging to analyse to consider intersectionality in depth.
Pricing Submission | Program | A Price Submission is a requirement of water corporations to demonstrate efficient and justified operating costs that determine the prices set for customers. The Essential Services Commission requires us to use this process to understand what our customers value and make their pricing determination for our business. | For Review | Yes | We included any notable gender differences observed through community engagement in our final 2023-28 Price Submission Engagement Report for decision-makers to consider. We have captured actions to enhance the GIA for the next price submission. Our Board included an additional success outcome for the 2023-28 Price Submission specifying that decision-makers have considered the available gendered information in their decision-making. We shared our approach for undertaking a GIA on the Price Submission process with the Essential Services Commission and other industry stakeholders. We have begun strengthening our gender data collection in our engagement programs to build additional gender breakdown into future reporting. | Yes | Intersectionality was considered and while data is collected on multiple demographics as part of our engagement approach, the way it's collected makes it challenging to analyse to consider intersectionality in depth.
Engagement Framework | Program | The Wannon Water Engagement Framework provides an approach and set of tools to support our employees and contractors to deliver genuine community engagement that builds capacity, strengthens relationships and informs decisions. | For Review | Yes | We included a gendered analysis of customer data collected when reporting on our 2022 and 2023 engagement programs, and have embedded this for future years. We tested the engagement questions in our 2023 annual engagement program for gender considerations. We have started a new approach to analysing all of our community engagement data sets by gender over the coming three years. We have started applying a gender lens in each step of our framework for specific projects, and have scheduled this for inclusion in the next full review of the framework itself (currently scheduled for 2025/26). We have begun engaging with similar organisations to understand their approaches for gender equality measures within their data sets. | Yes | Intersectionality was considered and while data is collected on multiple demographics as part of our engagement approach, the way it's collected makes it challenging to analyse to consider intersectionality in depth.
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.
Example(s)
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review | Yes | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated womens and all-gender secured changerooms and facilities for all womens and gender-diverse teams who hire Council sportsgrounds. | Yes | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are percieved as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.

## 2.1 Strategies and measures
Strategies and measures
Table 2.1 - Strategies and measures progress
Required | Required | Required | Recommended | Recommended | Recommended | Recommended
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | Relevant indicator(s)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Indicators key
List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. | [6 empty] | 1. 2. 3. 4. 5. 6. 7. | Gender composition of all levels of the workforce. Gender composition of governing bodies. Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender. Sexual harassment in the workplace Recruitment and promotion practices in the workplace. Availability and utilisation of terms, conditions and pratices relating to: - family violence leave - flexible working arrangements - working arrangements supporting employees with family or caring responsibilities Gendered segregation within the workplace
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | 1 | 2 | 3 | 4 | 5 | 6 | 7
1.0 Gender Composition of all levels of the workforce
Take up opportunities, internal and external to the organisation that support projects that improve industry gender recruitment pipelines | Ongoing | A number of activities to support industry pipelines have occurred, such as attendance at female targeted industry events (GHD), participation in female focused schools programs (Neil Porter Legacy), and progression of our own employees with internal and external development programs. This status has been selected as there we continue to identify opportunities to support projects and programs to improve industry gender recruitment pipelines. There is no delay or change from our planned actions. | We have seen a 3% increase in female representation through recruitment, demonstrating success of this strategy. Progress towards gender equality has been made. Refer to the status description and 3. Indicators tab for details. | Ongoing | People & Business Services; Community & Corporate Services | X
Create an internal gender stakeholder communications and engagement plan | Complete | Our internal gender stakeholder communication and engagement plan has been completed. Consultation with the Executive team and action owners relating to direction and accountability has occurred and is reported to Executive and Baord annually. This status has been selected as the action is complete. There is no delay or change from our planned actions. | Completion of the internal gender stakeholder communication and engagement plan demonstrates success for this strategy. Refer to the status description and 3. Indicators tab. | 2023-01-01 | People & Business Services | X
2.0 Gender composition of governing bodies
Gender composition of Wannon Water's governing body (our Board) is determined by The Minister for Water. | Void/cancelled | This status has been selected as Wannon Water does not appoint it's own Board Members. | No pre-identified success markers are included in the GEAP. There are no other evaluation markers within Wannon Water's operational activities to support this measure. Wannon Water supports the Board Observership (South West) program enhancing the skills of females within the region creating a pool of appropriate future candidates. | No timeline identified | N/A |  | X
3.0 Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender
Undertake a salary benchmarking exercise prior to the development of the next Enterprise Bargaining Agreement (EBA). | Complete | A salary benchmarking exercise was completed in late 2023. Data and initiatives have been considered to inform recommendations for Wannon Water's next EBA to improve pay gap. One initiative to reduce pay gap is to roll up allowances into base rate within certain Bands which will ensure the allowances paid in male dominant areas are also paid to female dominant areas in these bands. There are additional benefits such as efficencies with processing payroll and the initiative addresses a benchmarking pay gap within a deparment that has a high female composition. This status has been selected due to the action being complete. There is no delay or change from our planned actions. | A completed benchmarking report has been received demonstrating success for this strategy. Refer to the status description and 3. Indicators tab. | 2023-12-01 | People & Business Services |  |  | X
Develop an annual gender audit process to be accessed as a management tool to support the implementation of strategies and measures in this plan | Complete | A management reporting tool via Power BI has been updated and is currently in testing. The design has been structured to align with GEAP reporting requirements; and, management and Board Reporting. The data provides workplace insights to more easily identify and understand where gender disparities occur. Additionally, three Executive team working groups based on Recruitment Merit, Gender Pay Gap and Women's Development program have been established. The data provided through the management tool will to guide Wannon Water in decision making processes relating to gender. This status has been selected as the action is complete. There is no delay or change from our planned actions. This action is to support continuous improvement of Wannon Water's reporting alignment with GEAP requirements. | Development of a data dashboard to be used as a management tool to inform reporting has been completed, demonstrating success of this measure. Refinement on this strategy will contine. Refer to the status description and 3. Indicators tab. | 2022-12-01 | People & Business Services |  |  | X
4.0 Sexual harassment in the workplace
Develop a positive behaviours training program that incorporates sexual harassment, sexism, bias, showing respect, intersectionality and challenging inappropriate behaviours | In progress | Wannon Water have scoped and a training provider has been identified. An analysis of organisational needs and learning outcomes has been completed to inform the program. This program will be delivered to two audiences; employees and people managers. The program will commence in 2024, with planning and logistics underway. This status has been selected as the action is underway. There is no delay or change from our planned actions. Availability of providers may impact achieving the deadline. | Planning of this training has commenced, demonstrating we're on track to meet this strategy in the next reporting period. Refer to the status description. | 2024-05-01 | People & Business Services |  |  |  | X
5.0 Recruitment and promotion practices in the workplace
Mature our Learning and Development Framework to include a formal program of mentoring, secondments, sponsorships, projects and higher duties that support gender and intersectionality outcomes | In progress | Wannon Water offer a range of informal opportunities for mentoring, secondments and sponsorships. There are also several formal opportunities that occur through training and leadership programs and professional development opportunities. Our Reporting Tool (referenced in 3.0) has begun to provide insights into Projects and Higher Duties opportunities, allowing gender and intersectionality outcomes to be considered at an organisational level. Our Learning & development framework will be reviewed in 2024 to refocus our effects on leadership development. Work is underway to develop a customised, internal leadership program for high potential female employees in non-managerial roles, to best position them for future leadership roles. This status has been selected as the action is underway. There is no delay or change from our planned actions. Availability of resources may impact achieving the deadline on time. | Refinement of our Learning and Development Framework continues, demonstrating we're on track to meet the intent of this strategy in the next reporting period. Refer to the status description, and the 3. Indicators tab. | 2024-01-01 | People & Business Services |  |  |  |  | X
6.0 Availability and utilisation of terms, conditions and practices relating to family violence leave, flexible working arrangements, and working arrangements that support works with family or caring responsibilities
Monitor and report on use of family violence leave and flexible working arrangements (including caring) across all levels of the organisation by gender | Complete | Our annual reporting process provides insights into Family Violence Leave and Flexible Working Arrangements across all levels of the organisation by gender. The People Matter Survey also provides cultural insights to how employees feel regarding flexibility. This status has been selected as the action is complete. There is no delay or change from our planned actions. | Monitoring and reporting included in our annual Board reporting process demonstrates this strategy has been a success. Refer to the status description, and 3. Indicators tab. | 2023 | People & Business Services | [5 empty] | X
Review Individual Flexibility Working Arrangements to ensure best practice | Complete | A review of the Flexibility Working Arrangements Procedure has occurred, with changes including alignment to Fair Work Australia changes around the right to request flexibility. People managers have been educated and supported to implement these requirements in a timely manner. Enhanced transition to retirement opportunities were also added. This status has been selected as the action is complete. There is no delay or change from our planned actions. | Review and amendments to the Flexible Working Procedure have been completed and are available to employees, demonstrating the success of this strategy. Refer to the status description, and 3. Indicators tab. | 2023, 2025 | People & Business Services | [5 empty] | X
Review employee Family Violence Procedures to ensure best practice | Complete | A review of the Family Violence Procedure occurred, with changes aligning to Fair Work Australia changes regarding definitions, leave provision and providing greater guidance to people managers on providing workplace support and accommodations for those experiencing family violence. Wannon Water provide 20 days family violence leave exceeding minimim requirements. This status has been selected as the action is complete. There is no delay or change from our planned actions. | Review and amendments to the Family Violence Procedure have been completed and are available to employees, demonstrating the success of this strategy. Refer to the status description and 3. Indicators tab. | 2023, 2025 | People & Business Services | [5 empty] | X
Promote and share success stories of all genders accessing flexibility and paid parental leave | Complete | Employee stories were shared on the intranet and highlighted the different possibilities available to employees to enhance their work/life balance. Stories highlighted part-time employees and flexibility for health and wellbeing, family needs, and community service. In recognition of our efforts, conditions and culture, Wannon Water has also been certified as a Family Friendly Workplace. This status has been selected as the action is complete. There is no delay or change from our planned actions. | Sharing of employee stories including a series in late 2022, and highlighting employees with intersectionality through a range of measures deem this strategy a success. Refer to the status description, and 3. Indicators tab. | 2022, 2024, 2026 | Corporate & Community Services | [5 empty] | X
7.0 Gendered segregation within the workforce
Undertake a gender impact assessment of role design | Not started | This action has been selected as the action is not yet started. There is no delay or change from our planned actions. | No pre-identified success measures as this action is not yet due Refer to the status description. | 2024-06-01 | People & Business Services | [6 empty] | X
Develop and implement specific strategies for improved gender balanced teams across the organisation where there was a significant gender difference | In progress | Early considerations have been given to attraction, retention and recruitment processes, including increasing female representation within our field crews (operations and maintenance), and also male representation within our customer support teams. Further work is underway to redefine merit during our recruitment processes. This work aims to educate our people on how to select the best 'potential' for a role, versus the individual with the greatest experience, in an effort to increase equality for job applicants. This status has been selected as the action is in progress. There is no delay or change from our planned actions. | Early collaboration with certain gender segregated areas of the organisation is occuring, demonstrating we're on track to meet this strategy by the next reporting period. Refer to the status description. | 2024-06-01 | All departments, led by People & Business Services | [6 empty] | X
8.0 Other
Deliver education and training for managers and senior employees in relation to conducting Gender Impact Assessments | In progress | Education sessions provided to Senior Management and Executive team in Feb-2023 Tools, resources and general internal support have been provided to this group, to embed into BUA. Further education will be incorporated into the gender education program commencing in 2024 for all people managers. (row 19) | Training in February 2023 demonstrates the success of this strategy. Further GIA training will occur into the next reporting period. Refer to the status description. | 2023-06-01 | Corporate & Community Services
Develop and implement individual performance measures for managers that help create opportunities for improved gender equality | Complete | This has progressed as part of our Manager's Performance Measures through our performance management system, incorporating behavioural indicators for unconscious bias. A Gender Balanced Succession Plan has been implemented for Senior Management positions. The outcome of the plan has meant that for these roles, a gender balanced of at least 50% of females have been identified and career plans are being finalised. We are building the pipeline of females who will be more ready to take on senior roles. Working groups targeting Merit, Women's Development and the Gender Pay Gap, have also been created to provide management insights on potential opportunities to improve gender equality outcomes. This action has been selected as the action is complete. There is no delay or change from our planned actions. The Gender Balanced Succession Plan and Working Groups will continue for the foreseeable future. | New performance measures have been loaded into our Performance Management system, deeming this strategy a success. These measures will continually be refined. Refer to the status description. | 2023-07-01 | People & Business Services
Where appropriate, integrate GEAP strategies and actions into work and branch plans across Wannon Water to ensure ongoing implementation and support for outcomes. | Ongoing | Each Branch within Wannon Water has a Branch plan. At the time of reporting, 6 of the 12 (50%) of Branch Plans referenced gender equality or inclusion and diversity. Guidelines for Branch Plans have been updated to reflect a commitment to gender equality inititatives. When forming new committees, managers are required to where possible have gender balanced committees and working groups. This creates diversity of views and experience at the table and empowers women to have broader organisational knowledge and exposure, preparing them for future career opportunities. Gender related skills have been threaded through our core competencies which are scored and form part of the annual performance review. | The inclusion of Gender related actions in 50% of Branch Plans demonstrates we're on track to meet this strategy in the next reporting period. | 2024-03-01 | All Senior Managers
Select one
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.
Example(s)
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | Relevant indicator(s)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
Example: Address gaps identified in collecting intersectional data as part of employee and payroll systems | Complete | This strategy was implemented in March 2023. A payroll systems firm was engaged to upgrade our systems to support the collection of intersectional data in relation to sexual orientation, race, Aboriginality, religion, ethnicity, disability and gender identity. We have now begun collecting intersectional data and addressing the gaps identified in our 2021 audit. | Although originally anticipated for implementation in 2022, delays meant this strategy was implemented in March 2023. Intersectional data is being collected as part of new recruitments and promotions, and voluntary updates by existing staff. New intersectional data as part of our 2023 progress audit and future GEAPs will enable us to better understand intersectional gender equality in our organisation and areas for improvement. | 2022 | People and Culture Corporate Support | X | X | X |  | X | X | X

## 2.2 Resourcing your GEAP
Resourcing your GEAP
Table 2.2 - Allocation of resources to implement the strategies and measures in your GEAP
Recommended
You might consider some or all of the following, in addition to any other aspects you consider relevant: • Who implements the strategies and measures in your GEAP? What role do they perform at what level in your defined entity? • How many staff members/FTE are allocated to implementing the strategies and measures? • Was enough resourcing allocated to successfully implement your strategies and measures? If not, how will this be addressed?
Your Comments
The strategies and measures in Wannon Water's GEAP are dispersed throughout the business to maximise impact across all people facets of the orgasniations. The roles involved include: Wannon Water Executive Team Financial Controller Branch Manager - Corporate Services Manager - People & Wellbeing Diversity & Learning Officer Payroll Officers To meet the GEAP requirements, existing resources have been allocated to ensure actions are completed. This has required a re-prioritisation of internal resources, with budgets being allocated against actions accordingly. This approach will continue until the end of the current GEAP cycle. The Learning & Diversity officer was a specifically employeed in 2017 to build a strong foundation of I&D at Wannon Water. This resource was involved in the Pilot for GEAPS and continues to support the progression of initiatives.

## 3 Indicators
Workplace Gender Equality Indicators
Table 3 - Workplace gender equality indicators progress
Required | Required | Required | Recommended | [6 empty] | Recommended | Factors key:
|  |  | Factors | [7 empty] | a. b. c. d. e. f. g. | The size of the defined entity, including the defined entity's number of employees. The nature and circumstances of the defined entity, including any barriers to making progress. Requirements that apply to the defined entity under any other Act, including an Act of the Commonwealth. The defined entity's resources. The defined entity's operational priorities and competing operational obligations. The practicability and cost to the defined entity of making progress. Genuine attempts made by the defined entity to make progress.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
Gender composition of all levels of the workforce | Yes | Workforce Data In 2021, we had a 36% female representation, while in 2023, we had a 39% representation. The result demonstrates an overall 3% increase in our female workforce participation. This increase can be attributed to recruitment based activities such as using a gender decoder to craft job advertisements, and, developing pipeline talent through relationships with school and employment programs, including traineeships. We aim to continue this work into the future with our community partners, and influence the inclusion of gender considerations where appropriate. Our composition of the workforce has seen a favourable shift towards women at the -2 and -7 levels, and minor shifts at -3 and -4 levels. The -1, -5 and -6 levels have maintained their gender balance. With low reportable figures of employees that identify as self-described, analysis of impacts on this group remains challenging. Employee Experience Data There has been a 6% increase in female employees identifying with disability in 2023. There has been a 7% increase in male employees that speak a different language at home/with their community. These statistics demonstrate some incremental intersectional increases within our regional workforce. In relation to our Aspirational Targets outlined on page 6 of our Gender Equality Action Plan. We see 4% increase from 2021 to 2023 and are within 1% of our target in realtion to "My organisation uses inclusive and respectful images and language". It's pleasing to be within 1% of our target as we have made a consicious effort to share a broader range of stories across our employee base with intersectionality. We have seen a 4% decrease in "My Manager treats employees with dignity and respect" from 2021, to 2023. Through report sectioning we are able to identify this is attributed to a specific work group which is male dominant. Through this analysis we do not see this as a reflection on how women are feeling at Wannon Water. We are committed to working towards this issue to ensure all employees feel respected and valued at Wannon Water. GEAP Strategies & Measures Strategies and measures that have supported this progress include: - Recruitment and promotion practices - Take up opportunities, internal and external to the organisation that support projects that improve industry gender recruitment pipelines - Promote and share success stories of all genders accessing flexibility and paid parental leave - Flexibile Work Arrangements review | No | Yes | No | No | Yes | Yes | No | b) Our industry historically and through the nature of the work attracts males to service delivery roles, making progress more challenging for these roles. Role design is complex to change e) The competing priorities of focus such as regulatory compliance, best practice changes, training and service delivery to advance gender equality within the organisation can be challenging. f) Our approach to achieving equality is through attrition and the creation of new roles. This leads to slower progress while supporting our workforce culture.
Gender composition of governing bodies | No | Wannon Water Board appointed by the Minster for Water. Changes to our Board in 2023 are a result of Board members pursuing political aspirations, resulting in two vacancies, that were not filled by 30 June 2023. | No | No | No | No | No | No | No | N/A
Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender | Yes | Workforce Data In 2021, Wannon Water reported an overall Mean Base Salary Pay Gap of 12.9%, while in 2023, it's reduced to a 12% gap. This base salary pay gap is impacted by gender composition. The number of women employed at Wannon Water increased by 18 between 2021 and 2023, whereas the number of men increased by 9. The greatest increase for women was in full time ongoing employment (13) and greatest increase for men was in full time temporary employment (6). The pay gap for women employed in part time ongoing positions increased in favour of women by 6.7%. The number of men in part time positions decreased by 1. The average remuneration for part time women remained stable at $77.5K (vs. $79.5K in 2021). The pay gap for women employed in full time ongoing positions decreased by 3.3%, due to womens average pay increasing by $4.6K compared to Mens average pay increased by $1.7K between 2021 and 2023. This is attributed to having more women in higher earning roles, such as: - The number of women with over $100K base salary increased from 8 to 12. - The number of women earning between $80K - $100K increased from 7 to 14. This also demonstrates an upward shift in women’s roles within the organisational structure. The Mean Base Salary Pay Gap by level to the CEO demonstrates increases at the -1, and -2 levels. The-1 changes can be attributed to the Work Value Assessment outcomes determined by the Victorian Public Sector Commission Work Value Assessments. Gender composition of -1 roles show only one female at -1 and 4 males at -1. Pay increases in this level have impacted pay gap. We applied a work value assessment process to the -2 levels to value the role, rather than the individual. Modifications to remuneration are being implemented as identified and make this levels remuneration for objective rather than subjective. Decreases in Mean Base Salary Pay Gap by level to the CEO were achieved at the -3, -4, -5 and -6 levels and support our data around females working in more senior roles and higher remuneration, than 2 years ago. The overall Mean Total Remuneration Pay Gap by Gender has reduced from 18.9% in 2021, to 16.8% in 2023. We have attributed the total remuneration pay gap 2.1% reduction to a number of key intitiaves in the GEAP. These include: - females being offered and having the confidence to take higher duty roles - revised learning and development supports (secondments, sponsorships and mentoring) -more females in roles that manage a team or others which often relates to higher remuneration Continued in the cell below | No | Yes | No | Yes | Yes | Yes | No | b) Our industry historically and through the nature of the work attracts males to service delivery roles, making progress more challenging for these roles. Role design is complex to change. d) Limits on pricing submision that create revenue impacts reduce capacity to expend more on diversity initiatives (pay, training, pathways, etc) e) The competing priorities of focus such as regulatory compliance, best practice changes, training and service delivery to advance gender equality within the organisation can be challenging. f) Our approach to achieving equality is through attrition and the creation of new roles. This leads to slower progress while supporting our workforce culture.
Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender | Yes | Continued from the cell above Challenges we face in this space relate to the type of roles that attract males and attract overtime, more consistent higher duties, allowances. Roles that attract females tend to be more administrative and do not attract these penalties or allowances. We continue to see this as a focal point. In addition to the Overall Mean Base Salary Pay Gap insights, the shift in the total remuneration pay gap has been predominantly in the areas of women in full time ongoing roles. Average total remuneration increased by $4.7K for women, whereas men increased by $2.1K. This category was also the greatest shift in women employed in the organisation, increasing by 13. The Mean Total Remuneration Pay Gap by level to CEO showed that: - men are getting paid higher at the -1 , and -2 levels. This can be attributed to organisational responsibilities, and a re-classification of levels for these (CGEPS) reporting purposes. Work Value Assessments have been implemented at the -1 level, while a modified approach to the Work Value Assessments has been applied internally at the -2 level. We expect these intiatives to support reduction of gender pay gap in future. - Small decreases at the -4 and -5 level are favourable towards women. - Increased pay gap at the -6 level (by 6.2%) and the -7 level (by 0.9%) are attributable to the nature of work in these role that attract compensable remuneration through overtime and on call penalties. These roles are generally filled by males. As we continue to address gender segregation, we hope to see shifts in the pay gap in these areas. Employee Experience Data There is no reportable data for this indicator under the Employee Experience Data provided. GEAP Strategies & Measures Wannon Water continue to work towards increasing females into roles that manage teams, people or major projects, and to reduce the pay gap. Actions taken to contribute to achieve these goals include: - Undertaking a salary benchmarking exercise prior to the development of the next Enterprise Bargaining Agreement (EBA). - The development of an internal annual gender audit process to be accessed as a management tool to support the implementation of further strategies and measures in Wannon Water's GEAP In addition to the GEAP Strategies and Measures, we have created an internal data dashboard to provide real time data allowing us to track progress, rather than relying on data taken as a snapshot in time. | No | Yes | No | Yes | Yes | Yes | No | b) Our industry historically and through the nature of the work attracts males to service delivery roles, making progress more challenging for these roles. Role design is complex to change. d) Limits on pricing submision that create revenue impacts reduce capacity to expend more on diversity initiatives (pay, training, pathways, etc) e) The competing priorities of focus such as regulatory compliance, best practice changes, training and service delivery to advance gender equality within the organisation can be challenging. f) Our approach to achieving equality is through attrition and the creation of new roles. This leads to slower progress while supporting our workforce culture.
Sexual harassment in the workplace | Yes | Workforce Data A continual report of zero sexual harassment in the workplace demonstrates the exceptional level of behaviour of employees, and culture at Wannon Water. To maintain a great culture at Wannon Water, as per our GEAP Strategies and Measures, we intend to implement a positive behaviours training program prior to the next reporting period. Employee Experience Data Progress on the following People Matter Survey metric also demonstrates confidence for employees to call out any poor behaviour. The People Matter Survey asks employees "I feel safe to challenge inappropriate behaviour at work", with a response of "Agree/Strongly Agree" in 2021 of 77% (female) and 79% (male), and in 2023, a response rate of 89% (female) and 89% (male). This progress demonstrates both genders are feeling more comfortable to challenge inappropriate behaviour. GEAP Strategies & Measures Develop a positive behaviours training program that incorporates sexual harassment, sexism, bias, showing respect, intersectionality and challenging inappropriate behaviours. In addition to the strategies and measures outlined in our GEAP, Wannon Water are: - contributing to Respect 2040, a local initiative based on raising respect towards women, ran by Women's Health & Wellbeing Barwon South West - continue to participate in the local 16 Days of Activism Campaign, which aims to reduce gender-based violence - contributing to local networks ran by Local Government to provide an organisational view on how we support and educate employees on social and emotional issues, including gender-based violence | No | No | No | No | No | No | No
Recruitment and promotion practices in the workplace | Yes | Workforce Data Of the recruited employees in 2021, 56% were female, 44% were male; and in 2023, 53% were female and 48% were male. Attraction and appointment of more females in the 2023 year was attributed to language used in recruitment advertising through a gender decoder, workplace endorsements via organisations such as Work 180, flexibility offerings, and holding a reputation as an Employer of Choice. Other accrediations include Healthy Workplace Achievement, Family Friendly which support our employee of choice reputation. Employees who achieved permanent promotions in 2021showed 25% female and 75% male compated to 52% were female, and 48% were male in 2023. This indicates a 27% increase in female's receiving permanent promotions, and highlights female progression at a faster rate than males within the organisation. These statistics can be attributed to the Professional Development opportunities offered via the maturity of our Learning and Development Framework, and our Gender Balanced Succession Plan that will continue into the next reporting period. People who were awarded higher duties in 2021, consisted of female employees (28%), and males (72%) and opportunities for females were concentrated in the -5 and -7 Levels from the CEO. In 2023, there were 39% females and 61% males, and opportunities were dispersed across -1, -2, -3, -4, -5,-6 and -7 Levels from the CEO for female employees. This progress demonstrates an increase of females being provided and feeling confident in taking higher duties opportunities. The maturing of our Learning and Development Framework which has built confidence and experiences for females. The Gender Balanced Succession Plan has resulted in career plans for more females,continue to support gender intitatives to ready females for more senior roles at Wannon Water. Employee Experience Data The nature of comparing progress across 2021 and 2023 People Matter Survey questions has been challenging due to different survey questions. However, when asked "I have an equal chance at promotion in my organisation" in 2021, female employees responded with 50%, and Males 55%; in 2023, both female and male responded at a rate of 59%, showing progress in all genders. This response was higher than our competitors and VPSC. GEAP Strategies and Measures: - Take up opportunities, internal and external to the organisation that support projects that improve industry gender recruitment pipelines - Promote and share success stories of all genders accessing flexibility and paid parental leave - Integrate GEAP strategies and actions into branch plans across Wannon Water - Mature our Learning and Development Framework to include a formal program of mentoring, secondments, sponsorships, projects and higher duties that support gender and intersectionality outcomes These strategies and measures are also supported by the Employee Experience Data. In addition, to the Strategies and Measures outlined in our GEAP, we have commenced work on an internal Women's Development Program aimed at high potential female employees in non-managerial roles, to better position them for future leadership opportunities. | No | No | No | Yes | Yes | No | Yes | d) Opportunities for career advancement thorugh professional development, higher duties are limited by service delivery capabilities, budgets, and adequate opportunities. e) Via recruitment practices in this reporting period, Wannon Water has continued to appoint using merit based principles for advertised roles. This allows us to meet service delivery requirements efficiently and effectively. g) The genuine effort to provide our existing female workforce higher duties and professional development opportunities demonstrates progress in relation to permanent promotions.
Availability and utilisation of terms, conditions and practices relating to: - family violence leave; and - flexible working arrangements; and - working arrangements supporting employees with family or caring responsibilities | Yes | Workforce Data There has been a consistent 0% access of Family Violence Leave in both 2021 and 2023. Flexible working arrangements are supported throughout the business, with the highest uptake for both males and females at the -7 Level to the CEO. Males accessing flexibility has remained consistent, while females accessing flexibility has increased by 13 employees over the reporting period. This may be attributed to male dominant field based roles having less ability to access some forms of flexible work. We are commnecing discussions with our field based employees around flexibility options for their roles, and expect to see changes in the category in the next reporting period. Senior Leader flexible work has been relatively consistent from 2021 to 2023. There are notable differences in men Working remotely (8 in 2021, and 2 in 2023), which is attributable to the workplace variations during and post COVID. Employee Experience Data The types of caring responsibilities have been relatively consistent across categories and years, with the only notable increase for both male (7%) and female (5%) employees being in the "None of the above" categories. There is a continual difference in male employees identifying as accessing part-time employment, 24% difference to female employees in 2021, and 29% difference to female employees in 2023. There is also a slight increase (6%) of female employees "Working from an alternate location". These statistics indicate that while offering flexibility to all roles, women are still primarily accessing flexibility to meet commitments outside the workplace. We have shared employee flexibility success stories with the organisation to highlight the different types of flexibility available to achieve work/life balance. GEAP Measures & Strategies We have completed all actions aligned with our measures and strategies for this category, including: - Monitor and report on use of family violence leave and flexible working arrangements (including caring) across all levels of the organisation by gender - Review Individual Flexibility Working Arrangements to ensure best practice - Review employee Family Violence Procedures to ensure best practice - Promote and share success stories of all genders accessing flexibility and paid parental leave In addition to the above measures and strategies, recognition of our efforts, conditions and culture, Wannon Water has been certified as a Family Friendly Workplace. As such, we have further committed to: - engaging with employees to inform considered changes to parental leave practices and communications - promoting community family and caring based activities such as International Day of Families, and National Carer's Week | No | No | No | No | Yes | No | No | e) offering an essential service, means that service delivery to customers cannot be compromised. At times this limits, or requires critical thinking in relation to how certain roles can access flexible work practices.
Gendered segregation within the workplace | Yes | Workforce Data Wannon Water has seen a 10% increase in female management representation during the reporting period when classified by the ANZSCO codes. In reality, our organisational data using head counts, tells us that we have only a 6% increase in women that are managing teams or people. Our aspirational target of 40% continues to be a focus and is supported by a Women's Development Program, Gender Balanced Succession Planning and a suite of professional development opportunities where gender balance is considered. The representation of women in the Community and Personal Service Workers sector has risen by 25%. In 2021, there was an equal gender split among these workers, but by 2023, 75% of employees were female. While this increase is positive for the organization overall, it highlights the ongoing issue of gender segregation in specific roles. Primarily, this shift can be attributed to a project currently underway. There has been little change in gender composition (less than 5%) in our professional, clerical and administrative workers, labourers, machinery operators and drivers, and technicians and trade workers. There has been positive gender composition change in roles such as Occupational health and Safety Advisors, Civil Engineers and Maintenance Planner roles. Employee Experience Data Due to low numbers of bullying and discrimination within the organisation, we have limited data to compare for this indicator. As an example, for the statement "During the last 12 months in your current organisation, have you personally experienced discrimination at work?", in both 2021, and 2023, men reported a 94% response rate of "No". Women in 2021 reported 91%, and in 2023, 94% reported "No". There is a small difference (less than 5%) across all other Employee Experience questions across years and between male and female responses, which demonstrates the great employee experience at Wannon Water, regardless of gender GEAP Measures & Strategies - Develop and implement specific strategies for improved gender balanced teams across the organisation where there was a significant gender difference - Promote and share stories for all genders accessing flexibility and paid parental leave. In addition to the above GEAP Measures and Strategies, further work is underway to: - redefine merit during our recruitment processes to educate our people on how to select the best 'potential' for a role, versus the individual with the greatest experience - develop pipeline opportunities to grow our own employees within gender segregated parts of the business, - develop and implement our Women's Development Program, and - implement a Gender Impact Assessment on Role Design to assist in understanding any gender based barriers to certain roles. | No | Yes | No | No | Yes | Yes | No | b) Our industry naturally attracts males to service delivery roles, making progress more challenging for these roles. This includes society's expectations and contributions to reducing gender segregation. e) The competing priorities on compliance, training and service delivery to advance gender equality within the organisation can be challenging f) Our approach to achieving equality is through attrition and the creation of new roles. This leads to slower progress while supporting our workforce culture.
Example(s)
Indicator | Confirm if progress made | Progress description | Factors | [6 empty] | Factors discussion
|  |  | a | b | c | d | e | f | g
Example 1: Recruitment and promotion practices in the workplace | Yes | Recruitment In our 2021 audit, women represented only 35% of new recruits in the year to 30 June 2021. In our 2023 progress audit, this rose 6% to 41%. In 2021, of the women we recruited, 17% were employed on a full-time permanent basis, 14% on a part-time permanent basis and 69% on fixed-term contracts. In 2023, 22% of women recruited were employed on a full-time permanent basis, 20% on a part-time permanent basis and 58% on fixed-term contracts. We were not able to collect non-binary or gender diverse data in 2021. Our employee and payroll systems have since been updated to collect improved gender-diverse data. This has been achieved through the implementation of strategy 5.2 under our 2021 Gender Equality Action Plan (GEAP): ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. As such, in 2023, our data showed that 2% of new recruits identified as non-binary or gender diverse. Our organisation argues that these figures, in conjunction with successful implementation of relevant GEAP strategies, contribute to progress against Indicator 5. Not only have we been able to notably increase our recruitment of women and gender diverse employees, but we have also been able to offer these new recruits more attractive contract conditions. Stable contracts will also support us to retain employees of all genders and move towards a more gender-balanced workforce in the future. Promotions Our 2021 audit showed that 25% of promotions in the 12 months to 30 June 2021 were awarded to women. These promotions occurred in the lower and middle levels of the organisation only, and not within the executive leadership team. Our 2023 progress audit showed that 30% of all promotions were awarded to women, an increase of 5%. Of these, 10% occurred in the higher levels of the organisation and were ongoing permanent roles. Our organisation historically has a very stable executive leadership team where roles tend to be longer-term contracts or ongoing positions, with few exits. We are pleased to see promotion at the higher level of our organisation into ongoing positions for women. In 2021, we were not able to collect promotion data for non-binary or gender-diverse employees. In 2023, our updated systems allowed us to collect this data. However, there were no promotions awarded to this staff cohort. We believe that a significant aspect of our success in increasing the proportion of promotions awarded to women has been our focus on improving secondment and higher duties opportunities for women and gender-diverse employees. The proportion of secondments awarded to women increased by 5% and the proportion of higher duties by 6% between our 2021 workplace gender audit and our 2023 progress audit. Data on higher duties opportunities for gender diverse and non-binary employees was not collected in 2021, therefore there is no measured change in the data. We consider these improvements, while small, to demonstrate measurable progress against the workplace gender equality indicator ‘recruitment and promotion practices in the workplace’. We also believe the uptick in career development opportunities for women and resulting increase in women’s share of promotions demonstrates that our strategic approach is effective. We hope to see similar improvements for gender diverse employees reflected in our 2025 data. | No | Yes | No | No | No | No | Yes | As a largely male-dominated industry we recognise we have started from a lower baseline for this indicator and there is further to go. Despite this, we have made genuine efforts to attract and recruit a more gender diverse workforce by implementing the strategies identified in our GEAP, in particular: strategy 5.2 ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. We note that we are two years into the four-year GEAP implementation period, and as such have not fully implemented all GEAP strategies. The majority of our strategies against this indicator remain in early implementation stage. We believe our genuine efforts to implement strategies against this indicator and measurable progress arising from the data, demonstrate progress against indicator 5.
Example 2: Sexual harassment in the workplace | No | Our 2021 Employee Experience Survey data showed that 7% of women and 4% of men who responded to the survey had experienced sexual harassment in the workplace, and of those 5% of women and 6% of men made a formal complaint. In 2023, our Employee Experience Survey data showed that 9% of women and 6% of men who responded to the survey reported having experienced sexual harassment in the workplace, an increase of 2% from 2021 for both cohorts. Of those, 9% of women and 10% of men indicated that they had made a formal complaint. Our 2023 Employee Experience Survey also indicated that women with disability were overrepresented among those who reported experiencing sexual harassment. We have initiated a review process to consider how we might address this between now and the 2025 reporting cycle. No respondents in our 2021 Employee Experience Survey identified as gender diverse. We also didn’t record any formal sexual harassment complaints in our 2021 workforce reporting data from employees of self-described gender. In our 2023 employee experience survey, 2% of respondents identified as non-binary or gender diverse. Of this cohort, 10% indicated experience of sexual harassment, with 50% of this group indicating that they had made a formal complaint. We note that these figures represent an increase in anonymous self-reporting of sexual harassment. This is concerning, as anonymous reporting tends to be more accurate than formal incident reporting processes. In analysing our 2021 and 2023 audit data, we found that our workforce reporting shows minimal change in terms of outcomes for formal complaints of sexual harassment. In 2021, our audit data showed that no outcome was reached for 70% of matters where the complainant was a woman, and 50% of matters where the complainant was a man. In 2023, our progress audit showed that of the incidents of sexual harassment reported by women, no outcome was reached for 65% of matters. This figure was 40% for men. We did not collect data on gender diverse and non-binary employees in 2021, nor their experience of sexual harassment. Our 2023 progress audit showed that of the incidents of sexual harassment reported by gender diverse and non-binary employees, no outcome was reached for 67% of matters. The enduring high levels of formal complaints with no outcome across our 2021 and 2023 audit data suggests that we have work to do in effectively and efficiently resolving sexual harassment complaints. The lack of outcomes for incidents of this type may contribute to our lack of progress in reducing sexual harassment. As a result of this analysis, we are reviewing our GEAP strategies and measures to consider how we might better respond to, and therefore hopefully reduce, sexual harassment in our organisation. We consider that the anonymous nature of the Employee Experience Survey data provides an accurate representation of sexual harassment. The increased sexual harassment reported via the Employee Experience Survey data indicates ‘no progress’ was made by our organisation against this indicator. | No | No | No | Yes | Yes | No | No | (e) Competing priorities and operational obligations Our organisation is a metro health service. During the recent covid-19 pandemic, Victoria’s public health system experienced unprecedented demand. In particular, rates of access to ICU and ventilation increased dramatically. As such, our organisation prioritised its public-facing service delivery. We directed the majority of our stretched resources externally to enable high-quality public health care. Demand outstripped supply, and already-stretched resources were directed to keeping ICU and general wards staffed. As a result, we were not able to deliver comprehensive in-person bespoke staff training in relation to sexual harassment, so instead delivered a low-cost e-learning module. We also lacked the resources to comprehensively review our internal sexual harassment processes. (d) Resources As described cell D9, our resources were significantly stretched due to an increase in demand for ICU services during the covid-19 pandemic. Competing priorities reduced the resources available for internal-facing programs, such as comprehensive sexual harassment training delivery and process review. For this reason, we focussed on low-cost strategies and measures in our GEAP, including delivering a sexual harassment e-learning module, circulating internal communications campaigns and encouraging staff to undertake the Employee Experience Survey. Our communications campaign focussed on drawing attention to existing sexual harassment policies including how the organisation will respond.

## Examples (hidden)
1 Gender impact assessments
| Title | Subject | Description | Status |  |  | Confirm if actions taken |  |  |  | Describe actions taken |  | Confirm intersectionality considered |  | Explain intersectional lens applied
| What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. |  |  | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. |  |  |  | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. |  | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. |  | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
| Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review |  |  | Yes |  |  |  | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated womens and all-gender secured changerooms and facilities for all womens and gender-diverse teams who hire Council sportsgrounds. |  | Yes |  | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are percieved as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.
2.1 Strategies and measures
| Strategies and measures | Status | Status description | Evaluation of success | [6 empty] | Timeline | Responsible | Relevant indicator(s)
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
| List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | [6 empty] | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator.
| Example: Address gaps identified in collecting intersectional data as part of employee and payroll systems | Complete | This strategy was implemented in March 2023. A payroll systems firm was engaged to upgrade our systems to support the collection of intersectional data in relation to sexual orientation, race, Aboriginality, religion, ethnicity, disability and gender identity. We have now begun collecting intersectional data and addressing the gaps identified in our 2021 audit. | Although originally anticipated for implementation in 2022, delays meant this strategy was implemented in March 2023. Intersectional data is being collected as part of new recruitments and promotions, and voluntary updates by existing staff. New intersectional data as part of our 2023 progress audit and future GEAPs will enable us to better understand intersectional gender equality in our organisation and areas for improvement. | [6 empty] | 2022 | People and Culture Corporate Support | X | X | X |  | X | X | X
3 Workplace Gender Equality Indicators
| Indicator | Confirm if progress made | Progress description | Factors | [6 empty] | Factors discussion
|  |  |  | a | b | c | d | e | f | g
| This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
| Example 1: Recruitment and promotion practices in the workplace | Yes | Recruitment In our 2021 audit, women represented only 35% of new recruits in the year to 30 June 2021. In our 2023 progress audit, this rose 6% to 41%. In 2021, of the women we recruited, 17% were employed on a full-time permanent basis, 14% on a part-time permanent basis and 69% on fixed-term contracts. In 2023, 22% of women recruited were employed on a full-time permanent basis, 20% on a part-time permanent basis and 58% on fixed-term contracts. We were not able to collect non-binary or gender diverse data in 2021. Our employee and payroll systems have since been updated to collect improved gender-diverse data. This has been achieved through the implementation of strategy 5.2 under our 2021 Gender Equality Action Plan (GEAP): ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. As such, in 2023, our data showed that 2% of new recruits identified as non-binary or gender diverse. Our organisation argues that these figures, in conjunction with successful implementation of relevant GEAP strategies, contribute to progress against Indicator 5. Not only have we been able to notably increase our recruitment of women and gender diverse employees, but we have also been able to offer these new recruits more attractive contract conditions. Stable contracts will also support us to retain employees of all genders and move towards a more gender-balanced workforce in the future. Promotions Our 2021 audit showed that 25% of promotions in the 12 months to 30 June 2021 were awarded to women. These promotions occurred in the lower and middle levels of the organisation only, and not within the executive leadership team. Our 2023 progress audit showed that 30% of all promotions were awarded to women, an increase of 5%. Of these, 10% occurred in the higher levels of the organisation and were ongoing permanent roles. Our organisation historically has a very stable executive leadership team where roles tend to be longer-term contracts or ongoing positions, with few exits. We are pleased to see promotion at the higher level of our organisation into ongoing positions for women. In 2021, we were not able to collect promotion data for non-binary or gender-diverse employees. In 2023, our updated systems allowed us to collect this data. However, there were no promotions awarded to this staff cohort. We believe that a significant aspect of our success in increasing the proportion of promotions awarded to women has been our focus on improving secondment and higher duties opportunities for women and gender-diverse employees. The proportion of secondments awarded to women increased by 5% and the proportion of higher duties by 6% between our 2021 workplace gender audit and our 2023 progress audit. Data on higher duties opportunities for gender diverse and non-binary employees was not collected in 2021, therefore there is no measured change in the data. We consider these improvements, while small, to demonstrate measurable progress against the workplace gender equality indicator ‘recruitment and promotion practices in the workplace’. We also believe the uptick in career development opportunities for women and resulting increase in women’s share of promotions demonstrates that our strategic approach is effective. We hope to see similar improvements for gender diverse employees reflected in our 2025 data. | No | Yes | No | No | No | No | Yes | As a largely male-dominated industry we recognise we have started from a lower baseline for this indicator and there is further to go. Despite this, we have made genuine efforts to attract and recruit a more gender diverse workforce by implementing the strategies identified in our GEAP, in particular: strategy 5.2 ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. We note that we are two years into the four-year GEAP implementation period, and as such have not fully implemented all GEAP strategies. The majority of our strategies against this indicator remain in early implementation stage. We believe our genuine efforts to implement strategies against this indicator and measurable progress arising from the data, demonstrate progress against indicator 5.
| Example 2: Sexual harassment in the workplace | No | Our 2021 Employee Experience Survey data showed that 7% of women and 4% of men who responded to the survey had experienced sexual harassment in the workplace, and of those 5% of women and 6% of men made a formal complaint. In 2023, our Employee Experience Survey data showed that 9% of women and 6% of men who responded to the survey reported having experienced sexual harassment in the workplace, an increase of 2% from 2021 for both cohorts. Of those, 9% of women and 10% of men indicated that they had made a formal complaint. Our 2023 Employee Experience Survey also indicated that women with disability were overrepresented among those who reported experiencing sexual harassment. We have initiated a review process to consider how we might address this between now and the 2025 reporting cycle. No respondents in our 2021 Employee Experience Survey identified as gender diverse. We also didn’t record any formal sexual harassment complaints in our 2021 workforce reporting data from employees of self-described gender. In our 2023 employee experience survey, 2% of respondents identified as non-binary or gender diverse. Of this cohort, 10% indicated experience of sexual harassment, with 50% of this group indicating that they had made a formal complaint. We note that these figures represent an increase in anonymous self-reporting of sexual harassment. This is concerning, as anonymous reporting tends to be more accurate than formal incident reporting processes. In analysing our 2021 and 2023 audit data, we found that our workforce reporting shows minimal change in terms of outcomes for formal complaints of sexual harassment. In 2021, our audit data showed that no outcome was reached for 70% of matters where the complainant was a woman, and 50% of matters where the complainant was a man. In 2023, our progress audit showed that of the incidents of sexual harassment reported by women, no outcome was reached for 65% of matters. This figure was 40% for men. We did not collect data on gender diverse and non-binary employees in 2021, nor their experience of sexual harassment. Our 2023 progress audit showed that of the incidents of sexual harassment reported by gender diverse and non-binary employees, no outcome was reached for 67% of matters. The enduring high levels of formal complaints with no outcome across our 2021 and 2023 audit data suggests that we have work to do in effectively and efficiently resolving sexual harassment complaints. The lack of outcomes for incidents of this type may contribute to our lack of progress in reducing sexual harassment. As a result of this analysis, we are reviewing our GEAP strategies and measures to consider how we might better respond to, and therefore hopefully reduce, sexual harassment in our organisation. We consider that the anonymous nature of the Employee Experience Survey data provides an accurate representation of sexual harassment. The increased sexual harassment reported via the Employee Experience Survey data indicates ‘no progress’ was made by our organisation against this indicator. | No | No | No | Yes | Yes | No | No | (e) Competing priorities and operational obligations Our organisation is a metro health service. During the recent covid-19 pandemic, Victoria’s public health system experienced unprecedented demand. In particular, rates of access to ICU and ventilation increased dramatically. As such, our organisation prioritised its public-facing service delivery. We directed the majority of our stretched resources externally to enable high-quality public health care. Demand outstripped supply, and already-stretched resources were directed to keeping ICU and general wards staffed. As a result, we were not able to deliver comprehensive in-person bespoke staff training in relation to sexual harassment, so instead delivered a low-cost e-learning module. We also lacked the resources to comprehensively review our internal sexual harassment processes. (d) Resources As described cell D9, our resources were significantly stretched due to an increase in demand for ICU services during the covid-19 pandemic. Competing priorities reduced the resources available for internal-facing programs, such as comprehensive sexual harassment training delivery and process review. For this reason, we focussed on low-cost strategies and measures in our GEAP, including delivering a sexual harassment e-learning module, circulating internal communications campaigns and encouraging staff to undertake the Employee Experience Survey. Our communications campaign focussed on drawing attention to existing sexual harassment policies including how the organisation will respond.

## (Hidden) REF (hidden)
Policy | New | Yes | Select one | Yes
Program | For Review | No | Complete | No action taken
Service |  |  | In progress
Ongoing
Not started
Void/cancelled